## Feuil1
| 17/10 - 22/10 | 23/10 - 29/10 | 30/10 - 05/11 | 06/11 - 12/11 | 13/11 - 19/11 | 20/11 - 26/11 | 27/11 - 03/12 | 04/12 - 10/12 | 11/12 - 17/12 | 18/12 - 24/12 | 25/12 - 31/12 | 01/01 - 07/01 | 08/01 - 14/01
Research on 3D scanner
Installation of libraries
Research about point cloud
Compilation of the original code, group 1
Research on open cv + installation
First result
Improvement on the 3D reconstruted Mesh
Second result
Improvement on the GUI interface
Final result
Weekly Report
Final Report
Defense
in progress
completed